## Read me
Follow-up workbook (simulated)
Case study | Fictional. Example Bank and Vendor X are placeholders. All vendor answers, evidence, dates and scores are simulated.
Purpose | The follow-up to the initial vendor assessment: the bank's follow-up questions, the vendor's simulated replies, the re-rating of findings and risks, and the status of the go-live conditions.
Initial assessment | Folders 01 to 05 are unchanged. This workbook records what moved, what stayed and what is new.
Timeline | Request issued 12 Oct 2026. First vendor reply 6 Nov 2026. Second evidence batch 27 Nov 2026. Re-assessment closed 4 Dec 2026. Risk committee 11 Dec 2026. Conditions due 15 Jan 2027. Go-live target 1 Feb 2027.
Sheets | Summary, Findings, Risk register (four scores), Conditions, New actions, Follow-up questions (65), Re-asked (23 questions left unassessed in the initial assessment), Evidence log, Bank actions, Outside-in checks, Not requested, Controls (new), Regulatory map, ISO view (follow-up).
IDs | Follow-up questions: FU-AREA-NN (for example FU-IAM-01). In the traceability matrix they carry the prefix Q-. New: FND-23 to FND-33, REM-23 to REM-33, RR-18 to RR-21, EV-26 to EV-66, CR-29 to CR-33, BA-nn (bank actions), OS-nn (outside-in checks).
Reply types | Full, Partial, Declined, No reply describe the vendor's reply. Rating (Satisfactory, Partial, Gap, Not assessed) describes the assessor's view of the answer and the evidence.
Four risk scores | Inherent (before vendor controls), Initial current, Verified after the follow-up, Target. Risk falls only when evidence is verified, not when the vendor promises something.
Decision rules | Unchanged from the initial assessment: High findings closed before go-live, Medium within 90 days, a missing mandatory contract term for a critical service counts as High.
Not legal advice | Regulatory references are indicative. Verify against the official texts.
Input cell | Yellow fill: fill this in.

## Summary
Follow-up summary
All figures are formulas on the other sheets.
Follow-up questions by area | Questions | Satisfactory | Partial | Gap | Not assessed
Identity and access management | 5 | 3 | 2 | 0 | 0
Data security | 4 | 1 | 2 | 1 | 0
Cryptography and key management | 3 | 1 | 1 | 1 | 0
Application security | 7 | 2 | 5 | 0 | 0
Cloud security | 4 | 3 | 0 | 1 | 0
Network security | 3 | 3 | 0 | 0 | 0
Third-party risk | 4 | 0 | 3 | 0 | 1
AI security | 4 | 1 | 2 | 1 | 0
Vulnerability and security testing | 3 | 1 | 1 | 1 | 0
Security monitoring | 3 | 2 | 1 | 0 | 0
Incident response | 4 | 1 | 3 | 0 | 0
Business continuity and disaster recovery | 4 | 2 | 1 | 1 | 0
Privacy | 3 | 2 | 1 | 0 | 0
Governance, risk and compliance | 4 | 2 | 1 | 1 | 0
Change and configuration management | 3 | 2 | 1 | 0 | 0
People security and endpoints | 3 | 2 | 1 | 0 | 0
Infrastructure security | 2 | 2 | 0 | 0 | 0
Physical security | 2 | 0 | 1 | 0 | 1
Total | 65 | 30 | 26 | 7 | 2
Vendor reply to the 65 new questions
Full | 51
Partial | 11
Declined | 1
No reply | 2
Initial findings: outcome (22)
Closed | 8
Closed for go-live scope | 2
Risk accepted (signed) | 1
Partly closed | 6
Open | 3
Open (agreed, unsigned) | 2
Total | 22
Open findings by severity
| Initial | After follow-up
High | 5 | 2
Medium | 16 | 13
Low | 1 | 7
Total | 22 | 22
New findings in the follow-up |  | 11
Go-live conditions (10)
Verified | 2
Verified with residual | 2
In progress | 3
Partly met | 1
Not met | 2
Met or met with residual | 4

## Findings
Findings after the follow-up
Severity after the follow-up is the verified severity: Closed means closed, avoided or accepted with sign-off. For new findings, the severity is the original rating.
Finding | Title | Origin | Severity initial | Follow-up outcome | Severity after the follow-up | Evidence | What the vendor said or what we found | Next step
FND-01 | Wide standing access to connector credentials | Initial | High | Closed | Closed | EV-28, EV-26 | Read access limited to 3 platform security roles. Break-glass needs two-person approval. | None
FND-02 | Connector credentials rotated only once a year | Initial | High | Partly closed | Medium | EV-29, EV-30 | 90-day automated rotation. Revocation within 4 hours by the support desk. No self-service. | Reassess after the second rotation (Feb 2027). The bank can disable its own HR account at once
FND-03 | Standing support access from India with no transfer assessment | Initial | High | Partly closed | Medium | EV-26, EV-27, EV-31 | Just-in-time access live since 9 Nov. Transfer assessment for India provided. Masking for offshore staff by 30 Apr 2027. | Masking by 30 Apr 2027. DPO accepts the assessment with that condition
FND-04 | Undisclosed AI model provider with US hosting | Initial | High | Closed for go-live scope | Closed | EV-32, EV-33 | Provider named (Model Provider Z, US). Assistant disabled for the bank on 12 Nov. Full contract withheld. | Reopen before the assistant is ever enabled
FND-05 | Audit and inspection rights too limited | Initial | High | Open | High | EV-34 | Counter: two on-site audits a year with 10 working days' notice, unrestricted for regulators, pooled audits. | Not accepted by Legal. Escalated to the risk committee
FND-06 | Vendor's own PCI DSS attestation missing | Initial | Medium | Closed | Closed | EV-35, EV-04 | A qualified assessor letter says the vendor is out of scope (tokens only). Card Provider Y attestation valid. | Virtual cards can be enabled
FND-07 | No four-eyes control on the allowance rate table | Initial | Medium | Open | Medium | none | Planned for Q2 2027. Interim: a weekly change-log extract to Finance. | Finance reviews the log weekly (BA-05) until the feature ships
FND-08 | Assurance reports are outdated or narrow | Initial | Medium | Partly closed | Low | EV-36 | Bridge letter issued. Scope extension to visa, gifts and card modules in the 2027 audit. | Scope extension by 31 Dec 2027
FND-09 | No mutual TLS on bank-facing connections | Initial | Medium | Risk accepted (signed) | Closed | EV-37 | No mutual TLS. Private-key JWT, IP allow-list and 15-minute tokens. | Bank IT security signed the acceptance
FND-10 | Recovery targets not proven | Initial | Medium | Closed | Closed | EV-38 | Test on 18 Nov: 3 hours 40 minutes against 4 hours. | Repeat yearly
FND-11 | Guest data kept 24 months without deletion | Initial | Medium | Closed | Closed | EV-39 | 90-day automatic deletion live from 20 Nov. | None
FND-12 | Weak fourth-party notice, deletion and role classification | Initial | Medium | Open (agreed, unsigned) | Medium | EV-45 | Redline: 30-day email notice for all changes and a right to object. Visa agency retention to follow by Mar 2027. | Sign the contract before go-live
FND-13 | Free text not redacted from logs | Initial | Medium | Closed | Closed | EV-40 | Redaction live from 16 Nov. | None
FND-14 | Production data used in test | Initial | Medium | Partly closed | Low | EV-41 | Masked tooling live. Two months of logs show no production copies. | Check again at the next review
FND-15 | Exit arrangements weak | Initial | Medium | Open (agreed, unsigned) | Medium | EV-45 | Redline adds an insolvency clause and 24-hour credential revocation. Exit test planned for Jun 2027. | Sign the contract. Exit test by 30 Jun 2027
FND-16 | Slow incident notification and no assistance rate card | Initial | Medium | Partly closed | Medium | EV-46 | 48 hours offered. Rate card provided. | Legal decides on 48 hours
FND-17 | Insurer and assistance data handling | Initial | Medium | Closed | Closed | EV-42 | Retention cut to 12 months. Alert live. | None
FND-18 | Break-glass admin accounts not vaulted | Initial | Medium | Closed | Closed | EV-43 | Vaulted with two-person approval since 10 Nov. | None
FND-19 | VIP itineraries visible unmasked to support staff | Initial | Medium | Closed | Closed | EV-44 | Masking live from 17 Nov. Tested by Bank IT. | None
FND-20 | No regional hosting for non-EU staff | Initial | Medium | Closed for go-live scope | Closed | none | No regional hosting before 2028. The bank rolls out in the EU first. | Reopen before any non-EU rollout
FND-21 | Invoice files not signed and no call-back on bank-detail changes | Initial | Medium | Partly closed | Low | none | PGP signing from Q1 2027. The bank's call-back procedure was approved (BA-01). | Signing by 31 Mar 2027
FND-22 | Minor gaps in loyalty, discount codes and booker access reporting | Initial | Low | Open | Low | none | Reports in Q2 2027. | Track
FND-23 | US backup replication contradicts the EU-only claim | New | High | New (open) | High | EV-47, EV-66 | Cold backups replicate to a US region and have done since 2025. This contradicts claim V6 and Stage 2. | Stop the replication, delete the US copies and confirm the archive region is in the EU, or agree a transfer mechanism and assessment.
FND-24 | Security testing gaps | New | Medium | New (open) | Medium | EV-49, EV-50 | Three High scan findings are open beyond the 14-day target. Dynamic testing runs only quarterly. | Fix High findings within 14 days, run dynamic testing monthly and report ageing.
FND-25 | Branch protection can be bypassed | New | Medium | New (open) | Medium | EV-51 | Repository administrators can bypass review rules, and infrastructure code needs no second reviewer. | Enforce the rules for administrators and require a second reviewer for infrastructure code.
FND-26 | No software bill of materials | New | Low | New (open) | Low | EV-53 | The bill of materials is declined until Q2 2027. A top-20 library list was offered. | Provide the bill of materials when available.
FND-27 | Weak encryption key management | New | Medium | New (open) | Medium | EV-66 | Provider default keys, no customer-managed keys, key administration and use not separated, yearly rotation. | Separate key custodians, rotate keys at least yearly with evidence, and offer customer-managed keys for the bank's sensitive data.
FND-28 | SOC 2 exceptions and unmapped customer controls | New | Medium | New (open) | Medium | EV-60 | Two access-review exceptions, the cloud provider is carved out, and 14 customer controls are not yet assigned to bank owners. | Assign the 14 customer controls to bank owners and follow up the exceptions.
FND-29 | Incident exercise out of date | New | Low | New (open) | Low | EV-63 | The last tabletop exercise was in Mar 2025. The 2024 incident took 52 hours to notify. | Run a joint exercise in H1 2027 and share root cause summaries.
FND-30 | Offshore staff screening and endpoint protection | New | Medium | New (open) | Medium | EV-64 | Criminal checks in India are limited to five years. Support laptops have no endpoint data loss prevention, and USB is allowed at two of three sites. | Align screening where lawful, enable endpoint protection and block USB storage on support laptops.
FND-31 | Backup restore not tested | New | Medium | New (open) | Medium | EV-47 | The last restore test was in Aug 2025, and backups share the production account. | Run a restore test and keep backups in a separate account.
FND-32 | Liability cap far below the potential loss | New | Medium | New (open) | Medium | EV-61 | Cyber cover is EUR 10 million, but the contract cap is 12 months of fees (about EUR 0.4 million). | Agree a separate higher cap for data breach and confidentiality, or confirm other cover.
FND-33 | No public vulnerability disclosure programme | New | Low | New (open) | Low | OS-10 | No programme and no security.txt page. Planned for 2027. | Publish a security contact page and start a disclosure programme.

## Risk register
Risk register with four scores
L = likelihood, I = impact (1 to 5). Bands: 1 to 4 Low, 5 to 9 Medium, 10 to 15 High, 16 to 25 Very high. New risks were not identified in the initial assessment.
|  |  | Inherent |  |  |  | Initial current |  |  |  | Verified after the follow-up |  |  |  | Target
Risk | Risk description | Findings | L | I | Score | Band | L | I | Score | Band | L | I | Score | Band | L | I | Score | Band | Movement | Treatment | Owner
RR-01 | Stolen connector credential allows bulk reading of employee data | FND-01, FND-02, FND-09 | 4 | 5 | 20 | Very high | 3 | 5 | 15 | High | 2 | 4 | 8 | Medium | 2 | 4 | 8 | Medium | Down | Mitigate | Bank IT security
RR-02 | Standing support access from India exposes production data | FND-03, FND-30 | 4 | 4 | 16 | Very high | 4 | 4 | 16 | Very high | 3 | 4 | 12 | High | 2 | 4 | 8 | Medium | Down | Mitigate | Bank DPO and TPRM
RR-03 | Personal data reaches an undisclosed AI provider in the US | FND-04 | 3 | 4 | 12 | High | 4 | 4 | 16 | Very high | 1 | 4 | 4 | Low | 1 | 4 | 4 | Low | Down | Avoided (feature off) | Bank TPRM
RR-04 | Fraudulent or altered invoice reaches the ERP | FND-21 | 3 | 4 | 12 | High | 3 | 3 | 9 | Medium | 2 | 3 | 6 | Medium | 2 | 3 | 6 | Medium | Down | Mitigate | Bank Finance
RR-05 | Fraudulent allowance payments through rate-table changes | FND-07 | 3 | 3 | 9 | Medium | 3 | 3 | 9 | Medium | 2 | 3 | 6 | Medium | 1 | 3 | 3 | Low | Down | Mitigate (interim review) | Bank Finance
RR-06 | Card misuse or PCI non-compliance | FND-06 | 3 | 4 | 12 | High | 2 | 4 | 8 | Medium | 1 | 4 | 4 | Low | 1 | 4 | 4 | Low | Down | Mitigated | Bank Finance and TPRM
RR-07 | Outage or slow recovery of the platform | FND-10, FND-31 | 3 | 3 | 9 | Medium | 3 | 3 | 9 | Medium | 3 | 3 | 9 | Medium | 2 | 3 | 6 | Medium | Same | Mitigate | Bank TPRM
RR-08 | Late breach notice, costly incident assistance and a low liability cap | FND-16, FND-29, FND-32 | 3 | 4 | 12 | High | 3 | 4 | 12 | High | 3 | 4 | 12 | High | 2 | 3 | 6 | Medium | Same | Transfer (contract) and mitigate | Bank Legal
RR-09 | Excess retention and exposure of guest, log and test data | FND-11, FND-13, FND-14 | 4 | 3 | 12 | High | 3 | 3 | 9 | Medium | 2 | 3 | 6 | Medium | 2 | 2 | 4 | Low | Down | Mitigate | Bank DPO
RR-10 | Unseen fourth parties and late notice of change | FND-12 | 4 | 3 | 12 | High | 3 | 3 | 9 | Medium | 3 | 3 | 9 | Medium | 3 | 2 | 6 | Medium | Same | Mitigate | Bank TPRM
RR-11 | No effective audit or exit rights for a critical service | FND-05, FND-15 | 3 | 5 | 15 | High | 3 | 5 | 15 | High | 3 | 5 | 15 | High | 1 | 5 | 5 | Medium | Same | Transfer (contract) and mitigate | Bank Legal and Procurement
RR-12 | Reliance on outdated or narrow assurance reports | FND-08, FND-28 | 3 | 3 | 9 | Medium | 3 | 3 | 9 | Medium | 3 | 3 | 9 | Medium | 2 | 3 | 6 | Medium | Same | Mitigate | Bank TPRM
RR-13 | Leak of executive itineraries | FND-19 | 3 | 5 | 15 | High | 3 | 4 | 12 | High | 2 | 4 | 8 | Medium | 2 | 4 | 8 | Medium | Down | Mitigated | Bank IT security
RR-14 | Takeover of vendor break-glass admin accounts | FND-18 | 3 | 4 | 12 | High | 2 | 4 | 8 | Medium | 1 | 4 | 4 | Low | 1 | 4 | 4 | Low | Down | Mitigated | Bank TPRM
RR-15 | Non-compliance with local rules outside the EU | FND-20 | 3 | 3 | 9 | Medium | 3 | 3 | 9 | Medium | 2 | 3 | 6 | Medium | 2 | 3 | 6 | Medium | Down | Avoided (EU first) | Bank DPO and Compliance
RR-16 | Insurer and assistance data kept too long or interface fails | FND-17 | 3 | 3 | 9 | Medium | 2 | 3 | 6 | Medium | 1 | 3 | 3 | Low | 1 | 3 | 3 | Low | Down | Mitigated | HR benefits
RR-17 | Minor misuse of loyalty data, discount codes or booker accounts | FND-22 | 3 | 2 | 6 | Medium | 3 | 2 | 6 | Medium | 3 | 2 | 6 | Medium | 2 | 2 | 4 | Low | Same | Accept | Bank HR
RR-18 | Personal data stored outside the EU through US backup replication | FND-23 | 3 | 4 | 12 | High |  |  |  |  | 4 | 4 | 16 | Very high | 1 | 4 | 4 | Low | New | Mitigate (new, High) | Bank DPO
RR-19 | Application vulnerability reaches production through weak development controls | FND-24, FND-25, FND-26, FND-33 | 3 | 4 | 12 | High |  |  |  |  | 3 | 3 | 9 | Medium | 2 | 3 | 6 | Medium | New | Mitigate (new) | Bank IT security
RR-20 | Encryption keys weakly protected | FND-27 | 2 | 4 | 8 | Medium |  |  |  |  | 2 | 4 | 8 | Medium | 1 | 4 | 4 | Low | New | Mitigate (new) | Bank IT security
RR-21 | Misuse or data leakage by offshore support staff | FND-30 | 3 | 4 | 12 | High |  |  |  |  | 3 | 3 | 9 | Medium | 2 | 3 | 6 | Medium | New | Mitigate (new) | Bank DPO and TPRM
Risks by band (all rows)
| Band |  |  |  |  | Inherent |  |  |  | Initial |  |  |  | Follow-up |  |  |  | Target
| Very high |  |  |  |  | 2 |  |  |  | 2 |  |  |  | 1 |  |  |  | 0
| High |  |  |  |  | 12 |  |  |  | 4 |  |  |  | 3 |  |  |  | 0
| Medium |  |  |  |  | 7 |  |  |  | 11 |  |  |  | 13 |  |  |  | 12
| Low |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 4 |  |  |  | 9
Existing 17 risks only (same population in the initial assessment and the follow-up)
| Very high |  |  |  |  | 2 |  |  |  | 2 |  |  |  | 0 |  |  |  | 0
| High |  |  |  |  | 9 |  |  |  | 4 |  |  |  | 3 |  |  |  | 0
| Medium |  |  |  |  | 6 |  |  |  | 11 |  |  |  | 10 |  |  |  | 10
| Low |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 4 |  |  |  | 7

## Conditions
Go-live conditions after the follow-up
Action | Condition (due before go-live) | Status | Evidence | Residual or next step | Owner | Due
REM-01 | Secret read access limited to named roles, with approval and logging | Verified | EV-28, EV-26 | None | Vendor X | 15 Jan 2027
REM-02 | Credentials rotate at least every 90 days and the bank can revoke them | Verified with residual | EV-29, EV-30 | No self-service revoke. Vendor revokes in 4 hours. Reassess Feb 2027 | Vendor X | 15 Jan 2027
REM-03 | Just-in-time production access, masked data offshore, transfer assessment | Verified with residual | EV-26, EV-27, EV-31 | Masking by 30 Apr 2027 | Vendor X and Bank DPO | 15 Jan 2027
REM-05 | Unrestricted audit, access and inspection rights in the contract | Not met | EV-34 | Vendor counter is not unrestricted. Risk committee decision | Bank Legal | 15 Jan 2027
REM-08 | SOC 2 bridge letter | Verified | EV-36 | Scope extension by 31 Dec 2027 | Vendor X | 15 Jan 2027
REM-12 | Notice and a right to object for every subprocessor change | In progress | EV-45 | Agreed in the redline, not signed | Bank Legal | 15 Jan 2027
REM-15 | Insolvency and data-return clause, credentials revoked within 24 hours of the end | In progress | EV-45 | Agreed in the redline, not signed. Exit test by 30 Jun 2027 | Bank Legal | 15 Jan 2027
REM-16 | Incident notice within 24 hours and an assistance rate card | Partly met | EV-46 | 48 hours offered. Legal decides | Bank Legal | 15 Jan 2027
REM-23 | No data stored outside the EU (new High) | Not met | EV-47 | Vendor committed to delete by 15 Dec 2026. Evidence pending | Vendor X | 15 Jan 2027
REM-32 | Liability cap aligned with the potential loss (new) | In progress | EV-61 | Negotiating a higher cap for data breach | Bank Legal | 15 Jan 2027
Feature gates
Action | Feature | Status | Evidence | Note
REM-04 | AI assistant stays off for the bank | Verified (feature off) | EV-32 | Reopen FND-04 before any enabling
REM-06 | Virtual cards | Verified (can be enabled) | EV-35, EV-04 | Qualified assessor letter accepted

## New actions
New remediation actions from the follow-up
Action | Finding | Severity | Action | Owner | Due | Type | Evidence to verify | Status
REM-23 | FND-23 | High | Stop replication to the US archive, delete existing US copies and provide a deletion certificate. The vendor's own target is 15 Dec 2026. | Vendor X, verified by Bank DPO | 15 Jan 2027 | Pre-go-live | Deletion certificate and a new region diagram | Open
REM-24 | FND-24 | Medium | Fix High scan findings within 14 days, run dynamic testing monthly and report ageing. | Vendor X | 30 Apr 2027 | Within 90 days | Scan summaries | Open
REM-25 | FND-25 | Medium | Enforce branch protection for administrators and add a second reviewer for infrastructure code. | Vendor X | 30 Apr 2027 | Within 90 days | Rule screenshots | Open
REM-26 | FND-26 | Low | Provide the software bill of materials when available. | Vendor X | 30 Jun 2027 | Track | Bill of materials | Open
REM-27 | FND-27 | Medium | Separate key custodians, rotate keys at least yearly and offer customer-managed keys. | Vendor X | 30 Apr 2027 | Within 90 days | Key policy and rotation log | Open
REM-28 | FND-28 | Medium | Assign the 14 customer controls to bank owners and follow up the SOC 2 exceptions. | Bank TPRM and Vendor X | 30 Apr 2027 | Within 90 days | Control ownership list | Open
REM-29 | FND-29 | Low | Run a joint incident exercise and share root cause summaries. | Vendor X and Bank TPRM | 30 Jun 2027 | Track | Exercise report | Open
REM-30 | FND-30 | Medium | Align offshore screening where lawful, enable endpoint protection and block USB storage on support laptops. | Vendor X | 30 Apr 2027 | Within 90 days | Policy and endpoint report | Open
REM-31 | FND-31 | Medium | Run a restore test and move backups to a separate account. | Vendor X | 30 Apr 2027 | Within 90 days | Restore test record | Open
REM-32 | FND-32 | Medium | Agree a separate higher cap for data breach and confidentiality in the contract. | Bank Legal | 15 Jan 2027 | Pre-go-live | Signed contract clause | Open
REM-33 | FND-33 | Low | Publish a security contact page and start a disclosure programme. | Vendor X | 31 Jul 2027 | Track | Public page | Open

## Follow-up questions
Follow-up questions and vendor replies (simulated)
ID | Area | Question | Priority | Asked by | Linked to | Control | Evidence to request | Vendor reply (simulated) | Reply | Rating | Assessor notes
FU-IAM-01 | Identity and access management | How is privileged access to production systems granted (just-in-time, approval, expiry), and how long can a privileged session last? | Must | IT security | FND-03 | CR-09 | Privileged access tool configuration; 30-day access log | All production access goes through a privileged access tool. Requests need team-lead approval, expire after 4 hours and are recorded. Standing access was removed on 9 Nov 2026. | Full | Satisfactory | EV-26, EV-27. 30-day log shows no standing sessions. Closes part of FND-03.
FU-IAM-02 | Identity and access management | Provide the privileged account inventory and the date of the last privileged access review. | Must | Analyst | FND-01 | CR-09 | Account inventory; review record | Inventory of 41 privileged accounts. Last review on 30 Sep 2026, three accounts removed. | Full | Satisfactory | EV-26.
FU-IAM-03 | Identity and access management | How are service accounts and API keys inventoried, owned and rotated? Which belong to the bank's connector? | Must | IT security | FND-02 | CR-04 | Service-account inventory; rotation logs | Inventory with owners provided. Connector keys now rotate every 90 days by an automated job. The first rotation ran on 14 Nov 2026. | Full | Satisfactory | EV-29.
FU-IAM-04 | Identity and access management | Can the bank revoke the connector's credentials itself, and how fast can the vendor revoke on request? | Must | IT security | FND-02 | CR-04 | Revocation test record | No self-service revoke. The 24/7 support desk revokes within 4 hours. Tested on 19 Nov: 2 hours 10 minutes. | Partial | Partial | EV-30. The bank can disable its own HR service account at once, which is accepted as a compensating control.
FU-IAM-05 | Identity and access management | How is segregation of duties enforced for vendor staff who can both deploy code and access production data? | Should | TPRM lead | new | CR-09 | Segregation matrix; approved exceptions | Matrix provided. Two on-call engineer roles overlap, with an approved exception and extra logging. | Partial | Partial | EV-26. Exception approved by the vendor's security head. Sample reviewed.
FU-DAT-01 | Data security | Provide the data classification scheme and show how passport data and executive itineraries are labelled and handled. | Should | DPO | D2, D4 | CR-12 | Classification scheme; handling rules | Four levels. Passport numbers are Restricted with field-level encryption. Executive itineraries are Confidential with restricted visibility. | Full | Satisfactory | EV-66.
FU-DAT-02 | Data security | Provide the record of where each data type is stored and processed, including every location of backups and replicas. | Must | DPO | V6 | CR-14 | Data inventory; storage regions | Inventory provided. Production runs in two EU regions. Cold-archive backups replicate to a US region for long-term retention. | Full | Gap | EV-47. Contradicts the EU-only claim V6. New finding FND-23 (High).
FU-DAT-03 | Data security | How are backups and snapshots encrypted, and who can restore them? | Should | IT security | new | CR-31 | Backup encryption configuration; restore rights | AES-256 with provider-managed keys. Restore limited to five named engineers, with approval. | Full | Partial | EV-47. Key management weakness, see FND-27.
FU-DAT-04 | Data security | How do you stop personal data leaving through endpoints and email (data loss prevention)? | If applicable | Analyst | new | CR-32 | DLP configuration; device policies | DLP covers corporate email and cloud storage. Offshore support laptops have no endpoint DLP, and USB storage is allowed at two of three support sites. | Full | Partial | EV-64. See FND-30.
FU-CRY-01 | Cryptography and key management | Who manages the encryption keys for databases and backups, and can the bank use its own keys? | Must | IT security | FND-27 | CR-31 | Key management description | Provider default keys in the cloud provider's key service. Customer-managed keys are not offered. | Partial | Partial | EV-66. See FND-27.
FU-CRY-02 | Cryptography and key management | How are key custodians separated, and how often are keys rotated and revoked? | Must | IT security | FND-27 | CR-31 | Key policy; rotation log | Key administration and key use sit with the same platform team. Rotation is yearly. | Partial | Gap | EV-66. Fails the separation requirement. See FND-27.
FU-CRY-03 | Cryptography and key management | Provide the TLS configuration for public endpoints and for connections to the database and to fourth parties. | Should | Analyst | FND-09 | CR-13 | TLS configuration summary | Public endpoints: TLS 1.2 and 1.3 only, HSTS, no weak ciphers. Database connections use TLS 1.2. Supplier links use TLS 1.2 or higher. | Full | Satisfactory | EV-66. Matches the bank's outside-in scan (OS-02).
FU-APP-01 | Application security | Provide the secure development policy and a process diagram showing where security checks occur. | Must | Analyst | new | CR-29 | Policy; process diagram | Policy v4.2 and a pipeline diagram provided. | Full | Satisfactory | EV-48.
FU-APP-02 | Application security | Provide the latest static analysis and dependency scan summaries for the platform and the connector, with open High findings and their age. | Must | IT security | new | CR-29 | Scan summaries (SAST, SCA) | Scans run on every merge. Three High findings are open for 21, 25 and 40 days against a 14-day target. | Full | Partial | EV-49. See FND-24.
FU-APP-03 | Application security | How often is dynamic testing (DAST) run against a staging environment, and what were the last results? | Should | IT security | new | CR-29 | DAST summary | Quarterly. The last run was on 4 Oct 2026 with two Medium findings. | Full | Partial | EV-50. See FND-24.
FU-APP-04 | Application security | Show the branch protection and code review rules for production and infrastructure repositories. | Must | TPRM lead | new | CR-29 | Branch protection screenshots | One reviewer and passing checks are required. Repository administrators can bypass the rules. Infrastructure code needs no second reviewer. | Full | Partial | EV-51. See FND-25.
FU-APP-05 | Application security | Is automated secret scanning run on code repositories, and how are leaked secrets handled? | Must | IT security | V7 | CR-29 | Scanner configuration; incident records | Scanning with blocking on all repositories. Two secrets were found in 2026 and both were rotated within 24 hours. | Full | Satisfactory | EV-52.
FU-APP-06 | Application security | Provide the software bill of materials, or the list of critical third-party libraries, for the connector and platform. | If applicable | TPRM lead | new | CR-29 | Bill of materials or library list | Declined until Q2 2027. A list of the top 20 libraries with versions and licences was offered instead. | Declined | Partial | EV-53. See FND-26 (Low).
FU-APP-07 | Application security | Has a threat model been done for the connector and the support access path, and when was it last updated? | Should | IT security | new | CR-29 | Threat model summary | Connector threat model (STRIDE) from Mar 2026. None for the support access path. | Full | Partial | EV-48.
FU-CLD-01 | Cloud security | Provide the shared-responsibility matrix between the vendor and its cloud provider. | Should | Analyst | new | CR-30 | Responsibility matrix | Matrix provided. The vendor owns configuration, identity and data protection. | Full | Satisfactory | EV-54.
FU-CLD-02 | Cloud security | How is cloud configuration monitored for drift and misconfiguration (posture management)? | Should | IT security | new | CR-30 | Posture report | Daily posture scans. 97 percent of checks pass, four Medium items open. | Full | Satisfactory | EV-54.
FU-CLD-03 | Cloud security | Describe production, standby and backup regions, with a diagram of data replication between them. | Must | Analyst | V6 | CR-14, CR-30 | Region and replication diagram | The diagram shows two EU regions and a US archive region for cold backups, with a replication job running since 2025. | Full | Gap | EV-47, EV-66. FND-23.
FU-CLD-04 | Cloud security | How are production, staging and development environments separated, and who can access each? | Must | IT security | V10 | CR-30 | Environment separation description | Separate cloud accounts per environment. Production access only through the privileged access tool. | Full | Satisfactory | EV-54.
FU-NET-01 | Network security | Provide the network segmentation design: separation of web, application and database tiers, and administrative access. | Must | IT security | new | CR-30 | Segmentation diagram; rule summary | Three-tier network with default-deny rules. Diagram and rule summaries provided. | Full | Satisfactory | EV-55.
FU-NET-02 | Network security | Which perimeter controls protect public endpoints (web application firewall, DDoS protection, API gateway, rate limits)? | Must | IT security | new | CR-30 | Configuration summary | Web application firewall with managed rules, provider DDoS protection, an API gateway with rate limits. | Full | Satisfactory | EV-56.
FU-NET-03 | Network security | How is outbound traffic from production restricted to approved destinations? | Should | IT security | FND-09 | CR-30 | Egress rules | Outbound traffic leaves through a NAT gateway with an allow-list for fourth parties, reviewed twice a year. | Full | Satisfactory | EV-55.
FU-TPR-01 | Third-party risk | How do you assess your own suppliers (security review, questionnaire, reassessment), and how often? | Must | Analyst | FND-12 | CR-16 | Supplier assessment procedure | Tiered review at onboarding and yearly for critical suppliers (hosting, card, assistance). The AI provider was reviewed in Jun 2026 as a summary only. | Full | Partial | EV-57.
FU-TPR-02 | Third-party risk | Which suppliers receive personal data from the bank's tenant, and what contract terms flow down to them? | Must | DPO | FND-04, FND-12 | CR-16 | Supplier register; flow-down terms | Register updated to 11 suppliers, including the AI model provider. Standard flow-down terms. Visa agency amendment planned for Mar 2027. | Full | Partial | EV-57. FP11 confirmed.
FU-TPR-03 | Third-party risk | What is your concentration exposure to your cloud provider, and what is the plan if it fails? | Should | TPRM lead | new | CR-16 | Concentration statement; exit plan | One cloud provider, two regions. No multi-cloud plan. | Partial | Partial | Accepted as a known dependency. Recorded in the register.
FU-TPR-04 | Third-party risk | Provide your last two supplier incident notifications and how you responded. | If applicable | TPRM lead | new | CR-16 | Incident records | No reply. | No reply | Not assessed | Not chased: if applicable and low priority.
FU-AIS-01 | AI security | Name the AI model provider and its hosting region, and provide the contract and data processing terms for the bank's use case. | Must | TPRM lead | FND-04 | CR-28 | Provider name; contract excerpt | Model Provider Z, hosted in the US. A data processing excerpt was provided. The full contract is withheld as confidential. | Partial | Partial | EV-33.
FU-AIS-02 | AI security | Show that the AI assistant can be switched off for the bank's tenant, and demonstrate it. | Must | Analyst | FND-04 | CR-28 | Configuration; test session | Tenant-level switch. Turned off on 12 Nov 2026. A test session shows the assistant hidden and no calls to the provider. | Full | Satisfactory | EV-32. Observed by Bank IT.
FU-AIS-03 | AI security | How are prompts and outputs logged, masked and retained, and does free text with personal data reach the provider? | Must | DPO | FND-04 | CR-28 | Prompt handling description | Prompts are logged for 30 days. Names and emails are masked. Free text is not. | Full | Gap | EV-58. Weak evidence (statement). The feature stays off.
FU-AIS-04 | AI security | How are prompt injection and data leakage tested, and how is the feature classified under the EU AI Act? | Should | Compliance | new | CR-28 | Test summary; classification note | Internal red-team exercise in Jul 2026. Self-assessed as limited risk with a transparency notice. | Full | Partial | EV-58. To be checked by Compliance.
FU-VUL-01 | Vulnerability and security testing | Provide vulnerability scan coverage and patch deadlines, with the number of open Critical and High items. | Must | IT security | L3 | CR-23 | Scan summary | Weekly scans on all hosts. Targets: Critical 7 days, High 30 days. 0 Critical and 6 High open, 2 beyond target. | Full | Partial | EV-49.
FU-VUL-02 | Vulnerability and security testing | Provide the full penetration test report or the retest letter confirming the High findings were fixed. | Must | TPRM lead | EV-03 | CR-23 | Retest letter | The retest letter confirms both High findings were fixed on 22 Jul 2026. The full report is available on site under NDA. | Full | Satisfactory | EV-59.
FU-VUL-03 | Vulnerability and security testing | Do you run a vulnerability disclosure programme or bug bounty, and is there a security contact page? | If applicable | Analyst | new | CR-23 | Public page; programme details | No programme and no security.txt. Planned for 2027. | Full | Gap | Confirmed by the outside-in check OS-10. See FND-33 (Low).
FU-MON-01 | Security monitoring | Describe 24/7 security monitoring, escalation times, and coverage of identity, cloud and database logs. | Must | IT security | new | CR-15 | SOC contract summary; coverage matrix | Managed SOC 24/7. Critical alerts triaged within 15 minutes. Cloud, identity and application logs are covered, and database auditing covers personal data tables. | Full | Satisfactory | EV-66.
FU-MON-02 | Security monitoring | Are logs immutable, and how long are they kept (hot and cold)? | Should | IT security | FND-13 | CR-15 | Retention configuration | 90 days hot and 13 months cold in object-lock storage. | Full | Satisfactory | EV-40.
FU-MON-03 | Security monitoring | Can vendor administrator activity on the bank's tenant be sent to the bank's SIEM? | Should | IT security | FND-03 | CR-15 | Integration description | Audit events are available by API now. Streaming by syslog is planned for Q1 2027. | Partial | Partial | EV-66. Bank action BA-04.
FU-INC-01 | Incident response | Provide the incident response plan summary, the severity scale, and the date of the last exercise. | Must | Analyst | new | CR-24 | Plan summary; exercise record | Plan v3.1 aligned with ISO 27035. The last tabletop exercise was in Mar 2025. | Full | Partial | EV-63. See FND-29 (Low).
FU-INC-02 | Incident response | List security incidents in the last three years that affected customer data, with root cause and customer notification time. | Must | TPRM lead | new | CR-24 | Incident list | One incident in 2024: a misconfigured storage bucket exposed 800 itinerary files for 6 hours. Customers were notified after 52 hours. | Full | Partial | EV-63. Shows why 24 hours matters.
FU-INC-03 | Incident response | Will you notify the bank within 24 hours of confirming an incident affecting its data? If not, what can you commit to? | Must | Compliance | FND-16 | CR-24 | Contract language | 48 hours. A preliminary notice by email within 24 hours of detection is offered for major incidents, without details. | Partial | Partial | EV-46. Legal to decide.
FU-INC-04 | Incident response | Will you share the root cause report for incidents affecting the bank? | Should | Analyst | new | CR-24 | Contract language | Yes, a summary within 30 days. | Full | Satisfactory | EV-46.
FU-BCD-01 | Business continuity and disaster recovery | Provide the business impact analysis and the recovery objectives for the connector and the booking platform. | Should | Analyst | V5 | CR-24 | Impact analysis summary | 2026 analysis provided. Booking: 4 hours and 1 hour. Connector: 8 hours. | Full | Satisfactory | EV-66.
FU-BCD-02 | Business continuity and disaster recovery | Provide the latest disaster recovery test report, including actual recovery times. | Must | Analyst | FND-10 | CR-24 | Test report | Failover test on 18 Nov 2026: platform recovered in 3 hours 40 minutes, data loss 20 minutes. | Full | Satisfactory | EV-38.
FU-BCD-03 | Business continuity and disaster recovery | Provide the last backup restore test and show that backups are stored separately from production. | Must | IT security | new | CR-24 | Restore test record; account structure | Last restore test in Aug 2025. Backups share the production cloud account. | Full | Gap | EV-47. See FND-31.
FU-BCD-04 | Business continuity and disaster recovery | What is the plan if your cloud provider's region is unavailable for more than a day? | Should | TPRM lead | new | CR-24 | Continuity plan | Failover to the second EU region (tested). No plan for a provider-wide outage. | Partial | Partial | Accepted as a known dependency.
FU-PRV-01 | Privacy | Provide the record of processing for the bank's data and your process for data subject requests. | Must | DPO | new | CR-14 | Processing record; request procedure | Processor record and request procedure provided. Average handling time is 9 days. | Full | Satisfactory | EV-57.
FU-PRV-02 | Privacy | Provide transfer impact assessments for India, the US email and monitoring providers, and the AI provider. | Must | DPO | FND-03 | CR-14 | Impact assessments | Assessments for India, the email provider and the monitoring provider provided. None for the AI provider. | Partial | Partial | EV-31. The AI provider stays off.
FU-PRV-03 | Privacy | How is the bank's data deleted at contract end, including backups, and how is it evidenced? | Must | DPO | FND-15 | CR-12 | Deletion procedure; certificate sample | Deletion within 30 days. Backups age out in 35 days. A certificate is issued. | Full | Satisfactory | EV-39.
FU-GRC-01 | Governance, risk and compliance | Provide the SOC 2 exceptions, the carved-out subservice organisations and the customer controls you expect the bank to operate. | Must | Analyst | L1 | CR-23 | Exception list; customer control list | Two exceptions (access reviews done late twice). The cloud provider is carved out. 14 customer controls listed. | Full | Partial | EV-60. See FND-28.
FU-GRC-02 | Governance, risk and compliance | Provide the cyber insurance certificate and compare the cover with the liability cap in the contract. | Must | Finance | new | CR-33 | Insurance certificate; contract cap | Cover of EUR 10 million confirmed. The contract cap is 12 months of fees, about EUR 0.4 million. | Full | Gap | EV-61. See FND-32.
FU-GRC-03 | Governance, risk and compliance | Provide audited financial statements for the last two years and any going-concern notes. | Should | Finance | new | CR-33 | Audited accounts | Provided. Profitable, no going-concern note. | Full | Satisfactory | EV-62.
FU-GRC-04 | Governance, risk and compliance | Provide the anti-bribery and sanctions policy and training records, and say whether any investigation exists. | If applicable | Compliance | new | CR-33 | Policy; training records | Policy and 96 percent training completion. No investigations. | Full | Satisfactory | EV-66.
FU-CHG-01 | Change and configuration management | How are changes to production approved, tested and rolled back, and how are emergency changes handled? | Must | IT security | new | CR-29 | Change procedure | Change tickets with approval and automated gating. Emergency changes are reviewed within 48 hours. | Full | Satisfactory | EV-48.
FU-CHG-02 | Change and configuration management | How do you detect and handle configuration drift on the connector and platform baselines? | Should | IT security | new | CR-30 | Drift reports | Infrastructure is defined as code, with daily drift checks. | Full | Satisfactory | EV-54.
FU-CHG-03 | Change and configuration management | Will you notify the bank before changes that affect its integration (IP addresses, interfaces, new modules, new fourth parties)? | Must | Analyst | FND-12 | CR-27 | Contract language | 30 days for IP and interface changes. New modules are announced in release notes only. | Partial | Partial | EV-45.
FU-PPL-01 | People security and endpoints | What background screening applies to staff with access to customer data, including the offshore support team? | Must | Compliance | new | CR-32 | Screening policy; verification samples | Identity and employment checks for all staff. Criminal record checks in Ireland. For India, five years where lawful. | Full | Partial | EV-64. See FND-30.
FU-PPL-02 | People security and endpoints | Provide security training completion rates and phishing exercise results for staff with production access. | Should | Analyst | new | CR-32 | Training metrics | 98 percent training completion. Phishing click rate 3 percent. | Full | Satisfactory | EV-65.
FU-PPL-03 | People security and endpoints | How are leavers' access and laptops handled within 24 hours, and how are endpoints protected (EDR, disk encryption, local admin rights)? | Must | IT security | new | CR-32 | Leaver sample; endpoint report | Access removed within 24 hours in a sample of 10 leavers. EDR and disk encryption on all laptops. Local admin rights removed except for engineers. | Full | Satisfactory | EV-64.
FU-INF-01 | Infrastructure security | How are hosts hardened (baselines, golden images), and how are administrative ports exposed? | Should | IT security | new | CR-30 | Hardening baseline; admin access design | Hardened images based on an industry baseline. No public admin ports. Sessions are recorded. | Full | Satisfactory | EV-55.
FU-INF-02 | Infrastructure security | How can the cloud provider's staff reach customer data, and what controls apply? | Must | IT security | FH | CR-09 | Provider access description | Provider access to customer content is denied by default. Support access is logged and customer-approved. | Full | Satisfactory | EV-54.
FU-PHY-01 | Physical security | Provide the cloud provider's data centre assurance reports and confirm the locations used for the bank's data. | Should | Analyst | V6 | CR-30 | Provider reports; location list | 2025 provider reports provided. Locations: two EU regions and a US archive region. | Full | Partial | EV-47. The US location confirms FND-23.
FU-PHY-02 | Physical security | Describe physical access controls at your offices and the India support site. | If applicable | IT security | new | CR-32 | Site description | No reply. | No reply | Not assessed | Not chased: if applicable and low priority.

## Re-asked
Questions left unassessed in the initial assessment, re-asked in the follow-up
ID | Domain | Question | Vendor reply (simulated) | Reply | Rating | Assessor notes
A1 | Scope and service model | Is the service multi-tenant SaaS, single-tenant cloud, or self-hosted? Which edition and version are we buying? | Multi-tenant SaaS with a dedicated connector instance per client. The order form shows the enterprise edition. | Full | Satisfactory | EV-66.
A2 | Scope and service model | Which data categories will the service store or process (employee data, passport/ID numbers, financial data)? | The data inventory covers D1 to D16. Prompt logs and US archive backups were missing until the follow-up. | Full | Partial | EV-47. See FND-23.
B4 | Identity and sign-on | What session timeout, re-authentication and device or network restrictions apply? | Idle timeout 30 minutes, absolute 12 hours, re-authentication for payment settings. | Full | Satisfactory | EV-66.
C1 | Provisioning and leavers | How are accounts created (SCIM, API, manual, self-signup)? Is self-signup disabled? | Accounts are created from the roster through the connector. Self-signup is disabled. | Full | Satisfactory | EV-66.
C3 | Provisioning and leavers | How are role changes (movers) reflected in groups, roles and entitlements? | Role changes follow the HR record at the next nightly sync. | Full | Satisfactory | EV-66.
C4 | Provisioning and leavers | How are seats assigned and reclaimed, and are dormant accounts reported? | Monthly seat report. 12 dormant accounts were flagged in Sep and removed. | Full | Satisfactory | EV-66.
E1 | HR data sync | Which employee fields are received, and are they limited to the minimum needed? | The field mapping lists 14 fields. Gender and home address are not synced. | Full | Satisfactory | EV-66.
E2 | HR data sync | What method (REST, webhook, SFTP) and direction is used, and who initiates the connection? | REST over HTTPS, opened by the connector. SFTP is not used for the roster. | Full | Satisfactory | EV-66.
F1 | Approvals and policy | How are policy rules defined, approved and version-controlled? | Policy rules are versioned in the console with a change history. There is no second approval. | Full | Partial | See FND-07.
F2 | Approvals and policy | How is an approval request authenticated so it cannot be forged or replayed? | Approval messages are signed, with a nonce and a 5-minute expiry. Covered by the penetration test. | Full | Satisfactory | EV-59.
F3 | Approvals and policy | Is segregation of duties enforced (a requester cannot approve their own booking)? | A requester cannot approve their own trip. Test evidence provided. | Full | Satisfactory | EV-66.
F4 | Approvals and policy | How does the platform stop users who are not authorised bookers from creating bookings, and how is the sponsor's approval enforced for guest travel? | Only users with the booker role can create guest bookings. Sponsor approval is enforced in a workflow. | Full | Satisfactory | EV-66.
G3 | Financial sync | How are payment details and supplier data protected against tampering? | The vendor calls back for its own suppliers' bank-detail changes. For customers, the change letter is emailed, so the bank must apply its own call-back. | Full | Partial | Bank action BA-01. See FND-21.
H2 | Network and gateway | Which TLS versions and cipher policy are used? Is mutual TLS available for APIs? | TLS 1.2 and 1.3. Mutual TLS is not offered. Private-key JWT client authentication is offered. | Full | Partial | Accepted as a compensating control, see FND-09. EV-37.
H3 | Network and gateway | How are APIs authenticated (OAuth, keys), scoped and rate-limited? | OAuth 2.0 client credentials with scopes. Rate limit of 600 requests a minute per client. | Full | Satisfactory | EV-66.
I3 | Data protection | What are the retention, deletion and return rules at contract end, including backups? | Roster records are removed 90 days after leaving. Backups age out in 35 days. A deletion certificate is available. | Full | Satisfactory | EV-39.
I4 | Data protection | How is sensitive personal data (passport, ID, emergency contacts) protected (masking, field-level encryption)? | Passport numbers use field-level encryption. Passport copies for visas are kept for 90 days. | Full | Satisfactory | EV-66.
J2 | Logging and monitoring | Can we export logs to our SIEM in near real time? | Audit events are available by API now. Syslog streaming is planned for Q1 2027. | Full | Partial | BA-04.
J3 | Logging and monitoring | How are suspicious events detected, and how are we alerted? | A managed SOC alerts on anomalies. Customers are alerted by email within 1 hour of a confirmed incident. | Full | Satisfactory | EV-66.
K2 | Subprocessors | How are subprocessors assessed, and how are we notified of changes? | Suppliers are assessed at onboarding and yearly. Notice of changes is covered in the contract redline. | Full | Partial | EV-45, EV-57.
L3 | Assurance | What are the vulnerability management and patching timelines? | Critical 7 days and High 30 days patch deadlines. Six High items are open, two beyond the deadline. | Full | Partial | EV-49.
N2 | Contract terms | Does the vendor commit to cooperate with our competent and resolution authorities? | Cooperation with the bank's competent and resolution authorities is accepted in the bank addendum. | Full | Satisfactory | EV-45.
N6 | Contract terms | Will the vendor take part in our security awareness and resilience training where required? | Participation in the bank's training on request, up to two sessions a year. | Full | Satisfactory | EV-45.

## Evidence log
Evidence log, follow-up (simulated)
Evidence ID | Evidence item | Provided by | Date | Strength | Covers | Note
EV-26 | Privileged access tool configuration and approval workflow | Vendor X | 9 Nov 2026 | Medium | FU-IAM-01, FU-IAM-02, FU-IAM-05 | Screenshots
EV-27 | 30-day privileged access log extract | Vendor X | Oct to Nov 2026 | Strong | FU-IAM-01 | System export. No standing sessions
EV-28 | Secret read-access list (3 roles) and approval log | Vendor X | Nov 2026 | Strong | FND-01 | Verified by Bank IT security
EV-29 | Credential rotation job configuration and execution log | Vendor X | 14 Nov 2026 | Strong | FU-IAM-03 | First automated rotation
EV-30 | Revocation test record | Observed by Bank IT | 19 Nov 2026 | Strong | FU-IAM-04 | 2 hours 10 minutes
EV-31 | Transfer impact assessments: India support, email provider, monitoring provider | Vendor X | Nov 2026 | Medium | FU-PRV-02 | Vendor-authored, reviewed by the bank's DPO
EV-32 | AI assistant switch-off configuration and test session | Observed by Bank IT | 12 Nov 2026 | Strong | FU-AIS-02 | No calls to the provider seen
EV-33 | Data processing excerpt with the AI model provider | Vendor X | Nov 2026 | Medium | FU-AIS-01 | Full contract withheld
EV-34 | Vendor counter-proposal on audit rights (letter) | Vendor X | 6 Nov 2026 | Strong (document) | FND-05 | Two on-site audits a year, 10 working days' notice
EV-35 | Qualified assessor letter: vendor out of PCI DSS scope (tokens only) | Vendor X | Nov 2026 | Strong | FND-06 | Card Provider Y attestation remains valid (EV-04)
EV-36 | SOC 2 bridge letter, 1 Jan to 30 Sep 2026 | Vendor X | Oct 2026 | Strong | FND-08 | No new exceptions
EV-37 | Signed acceptance of compensating controls instead of mutual TLS | Bank IT security | Nov 2026 | Strong (internal) | FND-09 | Private-key JWT, IP allow-list, 15-minute tokens
EV-38 | Disaster recovery failover test report | Vendor X | 18 Nov 2026 | Strong | FU-BCD-02 | 3 hours 40 minutes, data loss 20 minutes
EV-39 | Guest-data retention configuration and deletion log | Vendor X | 20 Nov 2026 | Strong | FND-11, FU-PRV-03 | 90-day automatic deletion
EV-40 | Log redaction rule and sample log | Vendor X | 16 Nov 2026 | Strong | FND-13, FU-MON-02 | Free text redacted
EV-41 | Masked test-data pipeline configuration and two months of logs | Vendor X | Nov 2026 | Medium | FND-14 | No production copies in the period
EV-42 | Insurer data retention rule and interface alert sample | Vendor X | Nov 2026 | Medium | FND-17 | 12 months retention
EV-43 | Break-glass vault configuration and approval log | Vendor X | 10 Nov 2026 | Strong | FND-18 | Two-person approval
EV-44 | VIP profile masking configuration and test | Observed by Bank IT | 17 Nov 2026 | Strong | FND-19 | Support view masked
EV-45 | Contract redline: subprocessor notice, insolvency clause, 24-hour revocation | Vendor X | Nov 2026 | Medium (unsigned) | FND-12, FND-15, FU-CHG-03 | Agreed in principle, not signed
EV-46 | Incident notification offer (48 hours), root cause terms and assistance rate card | Vendor X | Nov 2026 | Medium | FND-16, FU-INC-03, FU-INC-04 | 24 hours not offered
EV-47 | Data inventory with storage regions and replication diagram | Vendor X | 6 Nov 2026 | Strong (document) | FU-DAT-02, FU-CLD-03, FU-BCD-03, FU-PHY-01 | Shows the US archive region
EV-48 | Secure development policy, pipeline diagram and change procedure | Vendor X | 6 Nov 2026 | Medium | FU-APP-01, FU-APP-07, FU-CHG-01 | Documents
EV-49 | Static and dependency scan summaries; vulnerability scan summary | Vendor X | Nov 2026 | Strong (export) | FU-APP-02, FU-VUL-01 | Three High findings beyond target
EV-50 | Dynamic testing summary | Vendor X | 4 Oct 2026 | Medium | FU-APP-03 | Quarterly
EV-51 | Branch protection rule screenshots | Vendor X | Nov 2026 | Medium | FU-APP-04 | Admins can bypass
EV-52 | Secret scanning configuration and 2026 incident records | Vendor X | Nov 2026 | Medium | FU-APP-05 | Two secrets rotated
EV-53 | List of the top 20 third-party libraries | Vendor X | Nov 2026 | Weak | FU-APP-06 | Not a full bill of materials
EV-54 | Shared-responsibility matrix, posture report, environment and drift evidence | Vendor X | Nov 2026 | Medium | FU-CLD-01, FU-CLD-02, FU-CLD-04, FU-CHG-02, FU-INF-02 | Documents and exports
EV-55 | Network segmentation diagram, rule summaries and hardening baseline | Vendor X | Nov 2026 | Medium | FU-NET-01, FU-NET-03, FU-INF-01 | Rule summaries only
EV-56 | Web application firewall, DDoS and API gateway configuration summary | Vendor X | Nov 2026 | Medium | FU-NET-02 | Summary
EV-57 | Supplier assessment procedure, supplier register (11) and processing record | Vendor X | Nov 2026 | Medium | FU-TPR-01, FU-TPR-02, FU-PRV-01 | Includes the AI provider
EV-58 | Prompt handling description and AI red-team summary | Vendor X | Nov 2026 | Weak | FU-AIS-03, FU-AIS-04 | Statements only
EV-59 | Penetration test retest letter | Independent test firm, via vendor | 22 Jul 2026 | Strong | FU-VUL-02, F2 | Both High findings fixed
EV-60 | SOC 2 exception list and customer control list (14 items) | Vendor X | Nov 2026 | Strong | FU-GRC-01 | Two exceptions
EV-61 | Cyber insurance certificate | Vendor X | Nov 2026 | Strong | FU-GRC-02 | EUR 10 million
EV-62 | Audited accounts, last two years | Vendor X | Nov 2026 | Strong | FU-GRC-03 | No going-concern note
EV-63 | Incident response plan summary, exercise record and incident list | Vendor X | Nov 2026 | Medium | FU-INC-01, FU-INC-02 | 2024 bucket incident
EV-64 | Screening policy, verification samples, leaver sample, endpoint report | Vendor X | Nov 2026 | Medium | FU-PPL-01, FU-PPL-03, FU-DAT-04 | Offshore gaps
EV-65 | Security training and phishing metrics | Vendor X | Nov 2026 | Medium | FU-PPL-02 | 98 percent completion
EV-66 | Vendor's physical architecture and security specification (submitted, unverified) | Vendor X | 6 Nov 2026 | Medium (vendor-authored) | Many R2 questions | See vendor-physical-architecture

## Bank actions
The bank's own actions (customer-side controls)
ID | Action | Owner | Status | Linked to
BA-01 | Call-back check for any change of the vendor's bank details | Bank Finance | Approved | FND-21
BA-02 | Conditional access and MFA policy for the platform application | Bank IT security | Done | FS, FND-09
BA-03 | Quarterly access review of bank-side booker accounts | Bank HR and IT | Planned | FND-22
BA-04 | Ingest vendor audit events into the bank's SIEM when streaming is available | Bank IT security | Planned (Q1 2027) | FU-MON-03
BA-05 | Weekly review of the allowance rate-table change log | Bank Finance | Started | FND-07
BA-06 | Runbook to disable the connector's service accounts at once | Bank IT security | Drafted | RR-01
BA-07 | Register of information entry and criticality record | Bank Compliance | Drafted | R1
BA-08 | Confirm whether the supervisor must be informed before signing | Bank Compliance | Open | R1
BA-09 | Decision on a data protection impact assessment | Bank DPO | In progress | R2
BA-10 | Review the India transfer assessment | Bank DPO | Reviewed, accepted with the masking condition | FND-03
BA-11 | Assign the 14 SOC 2 customer controls to bank owners | Bank TPRM | Open | FND-28
BA-12 | Fallback plan if the platform is unavailable (phone agent) | Bank HR | Planned | RR-07
BA-13 | Incident contact list agreed with the vendor | Bank TPRM | Done | RR-01

## Outside-in checks
Outside-in checks done by the bank (simulated results)
ID | Check | Result | Outcome
OS-01 | Sanctions and adverse media screening of the legal entity and owners | No matches | Closed
OS-02 | Public TLS configuration of the vendor's endpoints | TLS 1.2 and 1.3 only, HSTS on. Matches the vendor's statement | Closed
OS-03 | Email security records (SPF, DKIM, DMARC) | DMARC set to quarantine, not reject | Observation (Low)
OS-04 | Certificate and domain hygiene | Valid certificates, expiry in 62 days, no unexpected domains | Closed
OS-05 | External security rating | Stable, in the good range (simulated) | Closed
OS-06 | Public breach history, last three years | No public breach. The 2024 incident was not public | Observation
OS-07 | Company registry: ownership and legal entity | Matches the vendor's statements | Closed
OS-08 | Public subprocessor page | Lists 10 suppliers and omits the AI provider | Confirms FND-04
OS-09 | Credit and financial indicators | Low risk (simulated) | Closed
OS-10 | Security contact page (security.txt) | Absent | Confirms FND-33

## Not requested
Not requested, and why
Item | Reason
Source code review or access to repositories | The analyst asks for evidence, not code. Branch rules and scan summaries are enough
Running scans or tests against the vendor | Not an analyst's job and not permitted without agreement. The penetration test letter covers it
On-site visit to the cloud provider's data centres | Controls are inherited. The provider's assurance reports are requested instead
Physical security details of every vendor site | Asked once for the India support site, as an if-applicable item
Environmental, social and diversity reporting | No link to a risk in this case
E-discovery and legal hold procedures | Not relevant to a travel platform. Data return is covered in the contract
Container and Kubernetes configuration exports | Posture report and scan summaries are enough unless a finding points here
Full application security standard verification | Out of proportion for an analyst. Scan, test and review evidence is requested instead
Red team reports | Not expected from a vendor of this kind. Penetration test retest letter requested

## Controls (new)
New control requirements from the follow-up
CR ID | Area | Requirement | Risk addressed | Derived from | Questions | DORA | GDPR | ISO 27001:2022 Annex A | Other | Tier
CR-29 | Secure development | Code is built, reviewed, tested and released under a defined lifecycle with security testing, review rules that administrators cannot bypass, timely fixing of findings and tracked dependencies. | Vulnerable code reaches production | Follow-up items A and B; RR-19 | FU-APP-01, FU-APP-02, FU-APP-03, FU-APP-04, FU-APP-05, FU-APP-06, FU-APP-07, FU-CHG-01 | Art 9; Art 24 | Art 25; Art 32 | A.8.25; A.8.28; A.8.29; A.8.32 | OWASP ASVS (reference) | All tiers
CR-30 | Cloud and network platform security | The vendor's cloud platform is segmented, monitored for misconfiguration, protected at the perimeter and separated by environment, and keeps data in the agreed regions, backups included. | Data leaves the agreed regions or the platform is misconfigured | Follow-up items 1 and 3; V6; RR-18 | FU-CLD-01, FU-CLD-02, FU-CLD-03, FU-CLD-04, FU-NET-01, FU-NET-02, FU-NET-03, FU-INF-01, FU-CHG-02, FU-PHY-01 | Art 9 | Art 32 | A.5.23; A.8.9; A.8.20; A.8.22; A.7.1 |  | All tiers
CR-31 | Key management | Keys are held in a managed key service with separated custodians, rotated on a schedule, and customer-managed keys are offered for sensitive data. | Keys misused or exposed | Follow-up item 2; RR-20 | FU-CRY-01, FU-CRY-02, FU-DAT-03 | Art 9 | Art 32(1)(a) | A.8.24 |  | All tiers
CR-32 | People and endpoint security | Staff with access to the bank's data are screened, trained and use protected endpoints, offshore staff included. | Insider misuse or leakage by support staff | Follow-up item 5; RR-21 | FU-PPL-01, FU-PPL-02, FU-PPL-03, FU-DAT-04, FU-PHY-02 | Art 9 | Art 32 | A.6.1; A.6.3; A.8.1; A.7.2 |  | All tiers
CR-33 | Vendor standing: finance, insurance, liability | Insurance, financial standing and liability terms match the potential loss, and the vendor has an anti-bribery and sanctions policy. | The vendor cannot cover a loss | Follow-up; RR-08 | FU-GRC-02, FU-GRC-03, FU-GRC-04 | Art 28(4); Art 30(2) | Art 28(1) | A.5.22; A.5.31 | Anti-bribery policy (R5) | All tiers
Existing control requirements extended by the follow-up questions
CR ID |  | Follow-up questions added
CR-04 |  | FU-IAM-03, FU-IAM-04
CR-09 |  | FU-IAM-01, FU-IAM-02, FU-IAM-05, FU-INF-02
CR-12 |  | FU-DAT-01, FU-PRV-03
CR-13 |  | FU-CRY-03
CR-14 |  | FU-DAT-02, FU-CLD-03, FU-PRV-01, FU-PRV-02
CR-15 |  | FU-MON-01, FU-MON-02, FU-MON-03
CR-16 |  | FU-TPR-01, FU-TPR-02, FU-TPR-03, FU-TPR-04
CR-23 |  | FU-VUL-01, FU-VUL-02, FU-VUL-03, FU-GRC-01
CR-24 |  | FU-INC-01, FU-INC-02, FU-INC-03, FU-INC-04, FU-BCD-01, FU-BCD-02, FU-BCD-03, FU-BCD-04
CR-27 |  | FU-CHG-03
CR-28 |  | FU-AIS-01, FU-AIS-02, FU-AIS-03, FU-AIS-04

## Regulatory map
Regulatory map, follow-up questions
DORA = Regulation (EU) 2022/2554. GDPR = Regulation (EU) 2016/679. ISO = ISO/IEC 27001:2022 Annex A. Article-level and indicative.
ID | Area | Question | DORA reference | GDPR reference | ISO 27001:2022 Annex A | Other reference
FU-IAM-01 | Identity and access management | How is privileged access to production systems granted (just-in-time, approval, expiry), and how long can a privileged session last? | Art 9 | Art 32 | A.8.2; A.5.18
FU-IAM-02 | Identity and access management | Provide the privileged account inventory and the date of the last privileged access review. | Art 9 | Art 32 | A.8.2; A.5.18
FU-IAM-03 | Identity and access management | How are service accounts and API keys inventoried, owned and rotated? Which belong to the bank's connector? | Art 9 | Art 32 | A.8.2; A.5.18
FU-IAM-04 | Identity and access management | Can the bank revoke the connector's credentials itself, and how fast can the vendor revoke on request? | Art 9 | Art 32 | A.8.2; A.5.18
FU-IAM-05 | Identity and access management | How is segregation of duties enforced for vendor staff who can both deploy code and access production data? | Art 9 | Art 32 | A.8.2; A.5.18
FU-DAT-01 | Data security | Provide the data classification scheme and show how passport data and executive itineraries are labelled and handled. | Art 9 | Art 5(1)(c); Art 32 | A.5.12; A.8.13; A.8.12
FU-DAT-02 | Data security | Provide the record of where each data type is stored and processed, including every location of backups and replicas. | Art 30(2)(b) | Arts 44 to 49 | A.5.34; A.5.12
FU-DAT-03 | Data security | How are backups and snapshots encrypted, and who can restore them? | Art 9 | Art 5(1)(c); Art 32 | A.5.12; A.8.13; A.8.12
FU-DAT-04 | Data security | How do you stop personal data leaving through endpoints and email (data loss prevention)? | Art 9 | Art 5(1)(c); Art 32 | A.5.12; A.8.13; A.8.12
FU-CRY-01 | Cryptography and key management | Who manages the encryption keys for databases and backups, and can the bank use its own keys? | Art 9 | Art 32(1)(a) | A.8.24
FU-CRY-02 | Cryptography and key management | How are key custodians separated, and how often are keys rotated and revoked? | Art 9 | Art 32(1)(a) | A.8.24
FU-CRY-03 | Cryptography and key management | Provide the TLS configuration for public endpoints and for connections to the database and to fourth parties. | Art 9 | Art 32(1)(a) | A.8.24
FU-APP-01 | Application security | Provide the secure development policy and a process diagram showing where security checks occur. | Art 9 | Art 25; Art 32 | A.8.25; A.8.28; A.8.29 | OWASP ASVS (reference)
FU-APP-02 | Application security | Provide the latest static analysis and dependency scan summaries for the platform and the connector, with open High findings and their age. | Art 9 | Art 25; Art 32 | A.8.25; A.8.28; A.8.29 | OWASP ASVS (reference)
FU-APP-03 | Application security | How often is dynamic testing (DAST) run against a staging environment, and what were the last results? | Art 9 | Art 25; Art 32 | A.8.25; A.8.28; A.8.29 | OWASP ASVS (reference)
FU-APP-04 | Application security | Show the branch protection and code review rules for production and infrastructure repositories. | Art 9 | Art 25 | A.8.25; A.8.32; A.8.4 | OWASP ASVS (reference)
FU-APP-05 | Application security | Is automated secret scanning run on code repositories, and how are leaked secrets handled? | Art 9 | Art 25; Art 32 | A.8.25; A.8.28; A.8.29 | OWASP ASVS (reference)
FU-APP-06 | Application security | Provide the software bill of materials, or the list of critical third-party libraries, for the connector and platform. | Art 9 | Art 25; Art 32 | A.8.25; A.8.28; A.8.29 | OWASP ASVS (reference)
FU-APP-07 | Application security | Has a threat model been done for the connector and the support access path, and when was it last updated? | Art 9 | Art 25; Art 32 | A.8.25; A.8.28; A.8.29 | OWASP ASVS (reference)
FU-CLD-01 | Cloud security | Provide the shared-responsibility matrix between the vendor and its cloud provider. | Art 9 | Art 32 | A.5.23; A.8.9
FU-CLD-02 | Cloud security | How is cloud configuration monitored for drift and misconfiguration (posture management)? | Art 9 | Art 32 | A.5.23; A.8.9
FU-CLD-03 | Cloud security | Describe production, standby and backup regions, with a diagram of data replication between them. | Art 30(2)(b) | Arts 44 to 49 | A.5.23; A.5.34
FU-CLD-04 | Cloud security | How are production, staging and development environments separated, and who can access each? | Art 9 | Art 32 | A.5.23; A.8.9
FU-NET-01 | Network security | Provide the network segmentation design: separation of web, application and database tiers, and administrative access. | Art 9 | Art 32 | A.8.20; A.8.22
FU-NET-02 | Network security | Which perimeter controls protect public endpoints (web application firewall, DDoS protection, API gateway, rate limits)? | Art 9 | Art 32 | A.8.20; A.8.22
FU-NET-03 | Network security | How is outbound traffic from production restricted to approved destinations? | Art 9 | Art 32 | A.8.20; A.8.22
FU-TPR-01 | Third-party risk | How do you assess your own suppliers (security review, questionnaire, reassessment), and how often? | Art 28(3); Art 28(4) | Art 28(2); Art 28(4) | A.5.19; A.5.21; A.5.22
FU-TPR-02 | Third-party risk | Which suppliers receive personal data from the bank's tenant, and what contract terms flow down to them? | Art 28(3); Art 28(4) | Art 28(2); Art 28(4) | A.5.19; A.5.21; A.5.22
FU-TPR-03 | Third-party risk | What is your concentration exposure to your cloud provider, and what is the plan if it fails? | Art 28(3); Art 28(4) | Art 28(2); Art 28(4) | A.5.19; A.5.21; A.5.22
FU-TPR-04 | Third-party risk | Provide your last two supplier incident notifications and how you responded. | Art 28(3); Art 28(4) | Art 28(2); Art 28(4) | A.5.19; A.5.21; A.5.22
FU-AIS-01 | AI security | Name the AI model provider and its hosting region, and provide the contract and data processing terms for the bank's use case. | Art 28(3); Art 30(2)(a) | Art 5(1)(b); Art 22 (if individuals are affected) | A.5.19; A.5.34 | ISO/IEC 42001, EU AI Act (to check)
FU-AIS-02 | AI security | Show that the AI assistant can be switched off for the bank's tenant, and demonstrate it. | Art 28(3); Art 30(2)(a) | Art 5(1)(b); Art 22 (if individuals are affected) | A.5.19; A.5.34 | ISO/IEC 42001, EU AI Act (to check)
FU-AIS-03 | AI security | How are prompts and outputs logged, masked and retained, and does free text with personal data reach the provider? | Art 30(2)(c) | Art 5(1)(b); Art 32 | A.5.34; A.8.11 | ISO/IEC 42001, EU AI Act (to check)
FU-AIS-04 | AI security | How are prompt injection and data leakage tested, and how is the feature classified under the EU AI Act? | Art 28(3); Art 30(2)(a) | Art 5(1)(b); Art 22 (if individuals are affected) | A.5.19; A.5.34 | ISO/IEC 42001, EU AI Act (to check)
FU-VUL-01 | Vulnerability and security testing | Provide vulnerability scan coverage and patch deadlines, with the number of open Critical and High items. | Art 9; Art 24 | Art 32(1)(d) | A.8.8; A.8.29
FU-VUL-02 | Vulnerability and security testing | Provide the full penetration test report or the retest letter confirming the High findings were fixed. | Art 9; Art 24 | Art 32(1)(d) | A.8.8; A.8.29
FU-VUL-03 | Vulnerability and security testing | Do you run a vulnerability disclosure programme or bug bounty, and is there a security contact page? | Art 9 | n/a | A.8.8
FU-MON-01 | Security monitoring | Describe 24/7 security monitoring, escalation times, and coverage of identity, cloud and database logs. | Art 10 | Art 32 | A.8.15; A.8.16
FU-MON-02 | Security monitoring | Are logs immutable, and how long are they kept (hot and cold)? | Art 10 | Art 32 | A.8.15; A.8.16
FU-MON-03 | Security monitoring | Can vendor administrator activity on the bank's tenant be sent to the bank's SIEM? | Art 10 | Art 32 | A.8.15; A.8.16
FU-INC-01 | Incident response | Provide the incident response plan summary, the severity scale, and the date of the last exercise. | Art 17; Art 30(2)(f) | Art 33(2) | A.5.24; A.5.26; A.5.27
FU-INC-02 | Incident response | List security incidents in the last three years that affected customer data, with root cause and customer notification time. | Art 17; Art 30(2)(f) | Art 33(2) | A.5.24; A.5.26; A.5.27
FU-INC-03 | Incident response | Will you notify the bank within 24 hours of confirming an incident affecting its data? If not, what can you commit to? | Art 17; Art 19; Art 30(2)(f) | Art 33(2) | A.5.24; A.5.26
FU-INC-04 | Incident response | Will you share the root cause report for incidents affecting the bank? | Art 17; Art 30(2)(f) | Art 33(2) | A.5.24; A.5.26; A.5.27
FU-BCD-01 | Business continuity and disaster recovery | Provide the business impact analysis and the recovery objectives for the connector and the booking platform. | Art 11; Art 12 | Art 32(1)(b); Art 32(1)(c) | A.5.30; A.8.13; A.8.14
FU-BCD-02 | Business continuity and disaster recovery | Provide the latest disaster recovery test report, including actual recovery times. | Art 11; Art 12 | Art 32(1)(b); Art 32(1)(c) | A.5.30; A.8.13; A.8.14
FU-BCD-03 | Business continuity and disaster recovery | Provide the last backup restore test and show that backups are stored separately from production. | Art 12 | Art 32(1)(c) | A.8.13
FU-BCD-04 | Business continuity and disaster recovery | What is the plan if your cloud provider's region is unavailable for more than a day? | Art 11; Art 12 | Art 32(1)(b); Art 32(1)(c) | A.5.30; A.8.13; A.8.14
FU-PRV-01 | Privacy | Provide the record of processing for the bank's data and your process for data subject requests. | Art 30(2)(c) | Art 30; Art 35; Arts 12 to 22 | A.5.34
FU-PRV-02 | Privacy | Provide transfer impact assessments for India, the US email and monitoring providers, and the AI provider. | Art 30(2)(b) | Arts 44 to 49 | A.5.34
FU-PRV-03 | Privacy | How is the bank's data deleted at contract end, including backups, and how is it evidenced? | Art 30(2)(c) | Art 30; Art 35; Arts 12 to 22 | A.5.34
FU-GRC-01 | Governance, risk and compliance | Provide the SOC 2 exceptions, the carved-out subservice organisations and the customer controls you expect the bank to operate. | Art 28(4); Art 30(2) | Art 28(1) | A.5.22; A.5.31; A.5.35
FU-GRC-02 | Governance, risk and compliance | Provide the cyber insurance certificate and compare the cover with the liability cap in the contract. | Art 28(4) | n/a | A.5.22
FU-GRC-03 | Governance, risk and compliance | Provide audited financial statements for the last two years and any going-concern notes. | Art 28(4) | n/a | A.5.22
FU-GRC-04 | Governance, risk and compliance | Provide the anti-bribery and sanctions policy and training records, and say whether any investigation exists. | Art 28(4) | n/a | A.5.31
FU-CHG-01 | Change and configuration management | How are changes to production approved, tested and rolled back, and how are emergency changes handled? | Art 9 | Art 32 | A.8.32; A.8.9
FU-CHG-02 | Change and configuration management | How do you detect and handle configuration drift on the connector and platform baselines? | Art 9 | Art 32 | A.8.32; A.8.9
FU-CHG-03 | Change and configuration management | Will you notify the bank before changes that affect its integration (IP addresses, interfaces, new modules, new fourth parties)? | Art 9 | Art 32 | A.8.32; A.8.9
FU-PPL-01 | People security and endpoints | What background screening applies to staff with access to customer data, including the offshore support team? | Art 9 | Art 32 | A.6.1; A.6.3; A.8.1
FU-PPL-02 | People security and endpoints | Provide security training completion rates and phishing exercise results for staff with production access. | Art 9 | Art 32 | A.6.1; A.6.3; A.8.1
FU-PPL-03 | People security and endpoints | How are leavers' access and laptops handled within 24 hours, and how are endpoints protected (EDR, disk encryption, local admin rights)? | Art 9 | Art 32 | A.6.1; A.6.3; A.8.1
FU-INF-01 | Infrastructure security | How are hosts hardened (baselines, golden images), and how are administrative ports exposed? | Art 9 | Art 32 | A.8.9; A.8.20
FU-INF-02 | Infrastructure security | How can the cloud provider's staff reach customer data, and what controls apply? | Art 9 | Art 32 | A.8.9; A.8.20
FU-PHY-01 | Physical security | Provide the cloud provider's data centre assurance reports and confirm the locations used for the bank's data. | Art 28(4) | Art 32 | A.7.1; A.7.2; A.5.23
FU-PHY-02 | Physical security | Describe physical access controls at your offices and the India support site. | Art 28(4) | Art 32 | A.7.1; A.7.2; A.5.23

## ISO view (follow-up)
ISO 27001 view, follow-up
Annex A controls tested by the follow-up questions. New = not in the initial ISO view. Coverage view only, not a Statement of Applicability.
Annex A control | Title | Theme | Follow-up questions | Question IDs | New since the initial assessment
A.5.12 | Classification of information | Organizational | 4 | FU-DAT-01, FU-DAT-02, FU-DAT-03, FU-DAT-04 | No
A.5.18 | Access rights | Organizational | 5 | FU-IAM-01, FU-IAM-02, FU-IAM-03, FU-IAM-04, FU-IAM-05 | No
A.5.19 | Information security in supplier relationships | Organizational | 7 | FU-TPR-01, FU-TPR-02, FU-TPR-03, FU-TPR-04, FU-AIS-01, FU-AIS-02, FU-AIS-04 | No
A.5.21 | Managing information security in the ICT supply chain | Organizational | 4 | FU-TPR-01, FU-TPR-02, FU-TPR-03, FU-TPR-04 | No
A.5.22 | Monitoring, review and change management of supplier services | Organizational | 7 | FU-TPR-01, FU-TPR-02, FU-TPR-03, FU-TPR-04, FU-GRC-01, FU-GRC-02, FU-GRC-03 | No
A.5.23 | Information security for use of cloud services | Organizational | 6 | FU-CLD-01, FU-CLD-02, FU-CLD-03, FU-CLD-04, FU-PHY-01, FU-PHY-02 | No
A.5.24 | Information security incident management planning and preparation | Organizational | 4 | FU-INC-01, FU-INC-02, FU-INC-03, FU-INC-04 | No
A.5.26 | Response to information security incidents | Organizational | 4 | FU-INC-01, FU-INC-02, FU-INC-03, FU-INC-04 | No
A.5.27 | Learning from information security incidents | Organizational | 3 | FU-INC-01, FU-INC-02, FU-INC-04 | Yes
A.5.30 | ICT readiness for business continuity | Organizational | 3 | FU-BCD-01, FU-BCD-02, FU-BCD-04 | No
A.5.31 | Legal, statutory, regulatory and contractual requirements | Organizational | 2 | FU-GRC-01, FU-GRC-04 | No
A.5.34 | Privacy and protection of PII | Organizational | 9 | FU-DAT-02, FU-CLD-03, FU-AIS-01, FU-AIS-02, FU-AIS-03, FU-AIS-04, FU-PRV-01, FU-PRV-02, FU-PRV-03 | No
A.5.35 | Independent review of information security | Organizational | 1 | FU-GRC-01 | Yes
A.6.1 | Screening | People | 3 | FU-PPL-01, FU-PPL-02, FU-PPL-03 | Yes
A.6.3 | Information security awareness, education and training | People | 3 | FU-PPL-01, FU-PPL-02, FU-PPL-03 | No
A.7.1 | Physical security perimeters | Physical | 2 | FU-PHY-01, FU-PHY-02 | Yes
A.7.2 | Physical entry | Physical | 2 | FU-PHY-01, FU-PHY-02 | Yes
A.8.1 | User endpoint devices | Technological | 3 | FU-PPL-01, FU-PPL-02, FU-PPL-03 | No
A.8.2 | Privileged access rights | Technological | 5 | FU-IAM-01, FU-IAM-02, FU-IAM-03, FU-IAM-04, FU-IAM-05 | No
A.8.4 | Access to source code | Technological | 1 | FU-APP-04 | Yes
A.8.8 | Management of technical vulnerabilities | Technological | 3 | FU-VUL-01, FU-VUL-02, FU-VUL-03 | No
A.8.9 | Configuration management | Technological | 8 | FU-CLD-01, FU-CLD-02, FU-CLD-04, FU-CHG-01, FU-CHG-02, FU-CHG-03, FU-INF-01, FU-INF-02 | Yes
A.8.11 | Data masking | Technological | 1 | FU-AIS-03 | No
A.8.12 | Data leakage prevention | Technological | 3 | FU-DAT-01, FU-DAT-03, FU-DAT-04 | Yes
A.8.13 | Information backup | Technological | 7 | FU-DAT-01, FU-DAT-03, FU-DAT-04, FU-BCD-01, FU-BCD-02, FU-BCD-03, FU-BCD-04 | No
A.8.14 | Redundancy of information processing facilities | Technological | 3 | FU-BCD-01, FU-BCD-02, FU-BCD-04 | No
A.8.15 | Logging | Technological | 3 | FU-MON-01, FU-MON-02, FU-MON-03 | No
A.8.16 | Monitoring activities | Technological | 3 | FU-MON-01, FU-MON-02, FU-MON-03 | No
A.8.20 | Networks security | Technological | 5 | FU-NET-01, FU-NET-02, FU-NET-03, FU-INF-01, FU-INF-02 | No
A.8.22 | Segregation of networks | Technological | 3 | FU-NET-01, FU-NET-02, FU-NET-03 | No
A.8.24 | Use of cryptography | Technological | 3 | FU-CRY-01, FU-CRY-02, FU-CRY-03 | No
A.8.25 | Secure development life cycle | Technological | 7 | FU-APP-01, FU-APP-02, FU-APP-03, FU-APP-04, FU-APP-05, FU-APP-06, FU-APP-07 | Yes
A.8.28 | Secure coding | Technological | 6 | FU-APP-01, FU-APP-02, FU-APP-03, FU-APP-05, FU-APP-06, FU-APP-07 | Yes
A.8.29 | Security testing in development and acceptance | Technological | 8 | FU-APP-01, FU-APP-02, FU-APP-03, FU-APP-05, FU-APP-06, FU-APP-07, FU-VUL-01, FU-VUL-02 | No
A.8.32 | Change management | Technological | 4 | FU-APP-04, FU-CHG-01, FU-CHG-02, FU-CHG-03 | No